## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2195-swen-261-08-C-hess
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) |  | RM; 2/24/2020; PASS
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. |  | WH; 2/24/2020; PASS
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. |  | WH; 2/24/2020; PASS
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. |  | ED; 2/29/2020; PASS
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. |  | MW; 3/1/2020; PASS
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) |  | RM; 2/29/2020; PASS
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). |  | MW; 3/1/2020; PASS
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page.
Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player.
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  | Only players waiting for an opponent will be displayed, there is no need to handle this error
Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game.
Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable.
Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable.
Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories.
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  | NL; 2/29/2020; PASS
As a Player I want to sign-out so that I can stop playing. | Given that I am signed in when I click the sign out[my name] button then I expect to be signed out |  | MW; 3/1/2020; PASS
| Given that I am signed in when I sign out then I expect to see the number of online players decrease by one. |  | NL; 2/29/2020; PASS
As a Player I want to drag and drop my piece so that I am able to execute my moves. | Given that it’s my turn when I click and hold on to one of my pieces then I expect to be able to pick up that piece. | Pass |  | Pass |  | Pass
| Given that I’m currently holding a piece when I drop a piece in an invalid spot then I expect that piece to go back to its original position and my turn is still ongoing | Pass |  | Pass |  | Pass
| Given that I’m currently holding my piece when I stop holding my mouse button then I expect to be able to drop that piece | Pass |  | Pass |  | Pass
| Given that I'm currently holding my piece when I move it over to any valid spot then I expect to be able to visually see that spot turn a different shade. | Pass |  | Pass |  | Pass
| Given that I'm not holding a piece when I do click and hold onto a piece then I expect that piece on the board to be empty. | Pass |  | Pass |  | Pass
As a Player, I want to move my piece so I that I can advance forward. | Given that it is my turn when I pick up a piece and place it in a valid empty spot then I expect the piece to be there when I drop it.
Given that it is my turn when I make a successful move then my opponent should be able to see my move.
Given that it is not my turn when I make any move then the system should not carry out my move.
Given that it is my turn when I move a piece on top of a piece then I expect the system to reject my move.
Given that it is my turn when I move a piece to an invalid spot then I expect the piece to return to its original spot and it’s still my turn.
Given that it is not my turn when I try to move a piece then I expect the piece to return to its original spot without affecting the board.
Given that it is my turn when I try to pick up my piece and drop it on its original spot then I expect my turn to continue.
As a Player, I want to perform a single jump move so that I can move my piece and capture and opponent’s piece | Given that I have the opportunity to make a jump when I try to make a move other than jumping a piece then I expect my piece to move back to its original spot and my turn is still ongoing.
Given that I have the opportunity to make a jump when I try to jump a piece then I expect the system to accept my move.
Given that I am not a king and have a jump available “behind” a piece when I try to make that jump using that piece then I expect the system to reject my move
Given that I am a king and a jump is available when I try to make a move besides any valid jump then I expect the system to reject my move.
Given that I have multiple jumps available when I try to make one of the jumps then I expect the system to accept my move.
Given that I have no available jumps when I try to make a jump then my piece returns to it’s original position
Given that there are two pieces in one of my diagonals when I try to do a simple move then I expect the system to accept my move
As a Player, I want to perform multiple jump moves so that I can move my piece and capture multiple opposing pieces. | Given that I am a piece when I choose to make multiple valid jumps then I expect the piece to execute the jumps and take the opponent pieces
Given that I am a piece when I am able to make different multiple jumps then I expect the user to be able to pick a jump to execute.
Given that I am a piece when I am able to make multiple jumps then I expect to not be able to make a simple move.
Given that I am a normal piece when I choose to make backward multiple jumps then I expect the system to reject my moves and for it to still be my turn.
Given that I am a piece when I make an invalid multiple jump then I expect the system to reject my move and for it to still be my turn.
As a player, I want to get to the king row so that I can become a king. | Given that any of my pieces end up on the opposite side of the board when it lands on the opposite row then I expect my piece to visually become a king (two pieces stacked on each other) and my turn ends.
As a Player, I want to be able to move my king in any direction (diagonally) so that I can capture more pieces. | Given that my piece has become a king when I make a move then I expect to be able to simple more in any diagonal direction.
Given that my piece has become a king when I make multiple jumps then I expect to be able jump in any direction.
Given that my piece has become a king when I make a simple jump then I expect to be able to jump in any direction
As a Player, I want to make a move after my opponent does so that I can respond to their move. | Given that it is my turn when I try to make a valid move then I expect the system to accept that move.
Given that it is not my turn when I try to make any move then I expect to not even be able to pick up my piece
Given that it is my turn when I make a valid move then I expect my opponents board to be updated as well.
Given that I have made a valid move when I click the Submit Turn button then I expect to end my turn and my opponent’s turn begins.
As a Player, I want to know that I’ve won’t when I captured all my opponent’s pieces so that I can play another game. | Given that all of my opponent’s pieces are gone when I clear their final piece then I expect a message to pop up saying I won’ the game and a button to redirect me back to the homepage.
Given that my opponent is unable to make a move when it is their turn then I expect a message to popup saying I won the game and a button to redirect me back to the homepage.
As a Player, I want to know that I've lost when all my pieces are captured so that I can play another game. | Given that all my pieces are captured when I lose then I expect a message to popup saying I lost and a button to redirect me back to home.
Given that I am unable to make a move when it is my turn then I expect a message to pop up saying I lost the game and a button to redirect myself back to the homepage.